## Sprint 1
SWE 443 - TEAM BLUE
SPRINT BURNDOWN CHART
|  |  |  | Week 1 |  |  |  |  | Week 2
| Backlog Item ID | User Stories / Bugs |  | 24-26 | 2017-03-27 | 2017-03-28 | 2017-03-29 | 2017-03-30 | 31-2 | 2017-04-03 | 2017-04-04 | 2017-04-05 | 2017-04-06
|  |  | Initial Estimate | Weekend | Mon | Tues | Wed | Thurs | Weekend | Mon | Tues | Wed | Thurs | Result
| 1 | GitHub Set Up | 2 | Week 1 24-26: 2 | Done | Legend
| 2 | Template and Directory Set Up | 1 | [10 empty] | Done | bar: Week 1 24-26
| 3 | User/Account/Bank Stubs | 1.5 | Week 1 24-26: 1.5 | Done |  |  | Missing at Start
| 4 | Create Account | 3 | Week 1 24-26: 1; Week 1 2017-03-27: 0.25; Week 1 2017-03-30: -1; Week 2 31-2: 2.75 | Done |  |  | Added to Sprint
| 5 | Deposit Money | 3 | Week 1 24-26: 2; Week 1 2017-03-27: 0.25; Week 1 2017-03-30: -1; Week 2 31-2: 1.75 | Done
| 6 | Modify Transaction | 3 | Week 1 2017-03-27: 1; Week 2 31-2: -2; Week 2 2017-04-03: 3 | Incomplete
| 7 | Transfer Money | 3 | Week 1 2017-03-29: 0.5; Week 2 2017-04-03: 2.5 | Done
| 8 | Withdraw Money | 3 | Week 1 24-26: 2.5; Week 1 2017-03-30: -1; Week 2 2017-04-03: 1.5 | Done
| 9 | SDMLib Integration (Auto-generate object/class diagrams) |  | Week 1 2017-03-29: -3; Week 1 2017-03-30: 3 | Done | Hours in Sprint
| 10 | Persistence Layer (includes create account, deposit, withdraw, transfer) |  | Week 1 2017-03-29: -8; Week 1 2017-03-30: 2; Week 2 31-2: 5.5; Week 2 2017-04-03: -1.5 | Incomplete |  | Initial Estimate: |  | 45.5
| 11 | Scenario Writing (8) | 5 | Week 1 24-26: 2; Week 1 2017-03-28: 2; Week 2 31-2: 0.25; Week 2 2017-04-03: 0.75 | Done |  | Added Hours: |  | 42.5
| 12 | Welcome Screen | 1 | [10 empty] | Done | Total Hours this Sprint: |  |  | 88 | bar: Week 1 2017-03-27
| 13 | Log In | 3 | Week 1 2017-03-28: 2; Week 2 31-2: 1 | Done |  |  | *not completely accurate
| 14 | Android Research w/ SDMLib (before we start implementing) | 10 | Week 1 24-26: 7; Week 1 2017-03-28: 1; Week 2 31-2: 2 | Done
| 15 | Mockups |  | Week 2 31-2: -6; Week 2 2017-04-04: 2; Week 2 2017-04-05: 2; Week 2 2017-04-06: 2 | Done
| 16 | Class Diagram | [11 empty] | Incomplete | Progress | bar: Week 2 31-2
| 17 | Transaction Log |  | Week 2 31-2: -8; Week 2 2017-04-06: 0.5 | Incomplete |  | Week 1 Progress: |  | 35.5
| 18 | Transaction Fee | [11 empty] | Done |  | Week 2 Progress: |  | 36 | bar: Week 2 2017-04-04 to Week 2 2017-04-05
| 19 | Bugs/Fixes/Optimizations from Week 1 |  | Week 2 31-2: -8; Week 2 2017-04-03: 2; Week 2 2017-04-04: 1; Week 2 2017-04-06: 1 | Incomplete | Total Progress: |  |  | 71.5
| 20 | Burndown Chart Updating/Other Scrum Master Tasks | 7 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | Done |  |  | *not completely accurate
|  | Remaining Hours | 45.5 | 25 | 22 | 16.5 | 26.5 | 24 | 35.25 | 26.5 | 24 | 20.5 | 16.5
|  | Ideal Trend | 45.5 | 40.95 | 36.4 | 31.85 | 27.3 | 22.75 | 18.2 | 13.65 | 9.1 | 4.55 | 0
Note on E5: Note: Effort calculated using Story Points assigned at Sprint Planning - Enter as a positive Integer
Note on S8: If something is missing at the start of Sprint Planning, place this color box in column E to indicate it was added after the start of the Sprint.
Note on S9: Format the cell of the day that a missing item was added to the Sprint with this color and add in an estimate of story points for the item.
Note on E14: If something is missing at the start of Sprint Planning, place this color box in column E to indicate it was added after the start of the Sprint.
Note on I14: Format the cell of the day that a missing item was added to the Sprint with this color and add in an estimate of story points for the item.
Note on E15: If something is missing at the start of Sprint Planning, place this color box in column E to indicate it was added after the start of the Sprint.
Note on I15: Format the cell of the day that a missing item was added to the Sprint with this color and add in an estimate of story points for the item.
Note on E20: If something is missing at the start of Sprint Planning, place this color box in column E to indicate it was added after the start of the Sprint.
Note on K20: Format the cell of the day that a missing item was added to the Sprint with this color and add in an estimate of story points for the item.
Note on E21: If something is missing at the start of Sprint Planning, place this color box in column E to indicate it was added after the start of the Sprint.
Note on K21: Format the cell of the day that a missing item was added to the Sprint with this color and add in an estimate of story points for the item.
Note on E22: If something is missing at the start of Sprint Planning, place this color box in column E to indicate it was added after the start of the Sprint.
Note on K22: Format the cell of the day that a missing item was added to the Sprint with this color and add in an estimate of story points for the item.
Note on E23: If something is missing at the start of Sprint Planning, place this color box in column E to indicate it was added after the start of the Sprint.
Note on M23: Format the cell of the day that a missing item was added to the Sprint with this color and add in an estimate of story points for the item.
Note on E24: If something is missing at the start of Sprint Planning, place this color box in column E to indicate it was added after the start of the Sprint.
Note on K24: Format the cell of the day that a missing item was added to the Sprint with this color and add in an estimate of story points for the item.

## Sprint 1.5
SWE 443 - TEAM BLUE
SPRINT BURNDOWN CHART
|  |  |  | Week 1 |  |  |  |  | Week 2
| Backlog Item ID | User Stories / Bugs |  | 2017-04-05 | 2017-04-06 | 7-9 Apr | 2017-04-10 | 2017-04-11 | 2017-04-12 | 2017-04-13 | 14-16 Apr | 2017-04-17 | 2017-04-18
|  |  | Initial Estimate | Wed | Thurs | Weekend | Mon | Tues | Wed | Thurs | Weekend | Mon | Tues | Result
| 1 | Modify Transaction (Undo) | 1 |  | -3 | 3 |  |  |  | 1 |  |  |  | Done | Legend
| 2 | Persistence Layer (includes create account, deposit, withdraw, transfer) | 2 | [5 empty] | 2 |  |  |  |  | Done
| 3 | Class Diagram | 2 |  |  |  |  | 2 | [5 empty] | Done |  |  | Missing at Start
| 4 | Transaction Log + Transaction Class | 8 |  |  |  |  | -1 | 1 |  |  | 7 | 1 | Done |  |  | Added to Sprint
| 5 | Transaction Fee | 1 |  |  | 1 | [7 empty] | Done
| 6 | Transaction Sequence Diagram | 3 | [5 empty] | 2 |  |  |  | 1 | Done
| 7 | Android Integration + Start Android GUI | 16 |  |  |  |  | 0.75 |  | 2.25 | 8 | 2 | 3 | Done
| 8 | Sales Pitch/Presentation Planning and Completion | 4 | [9 empty] | 4 | Done
| 9 | General Refactoring (Classes, Tests) | 1 | [5 empty] | 1 |  |  |  |  | Done | Hours in Sprint
| 10 | Class Diagram | 2 |  |  |  |  | 2 | [5 empty] | Done |  | Initial Estimate: |  | 48
| 11 | Scenario Writing (Transaction Log) | 1 |  |  |  | 1 | [6 empty] | Done |  | Added Hours: |  | 4
| 12 | [12 empty] | - | Total Hours this Sprint: |  |  | 52
| 13 | [12 empty] | - |  |  | *not completely accurate
| 14 | [12 empty] | -
| 15 | [12 empty] | -
| 16 | [12 empty] | - | Progress
| 17 | [12 empty] | - |  | Week 1 Progress: |  | 13.25
| 18 | [12 empty] | - |  | Week 2 Progress: |  | 38.75
| 19 | [12 empty] | - | Total Progress: |  |  | 52
| 20 | Burndown Chart Updating/Other Scrum Master Tasks | 7 | 0.5 | 0.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1.5 | 0.5 | 0.5 | Done |  |  | *not completely accurate
|  | Remaining Hours | 48 | 47.5 | 50 | 44.5 | 43 | 38.75 | 32.25 | 28.5 | 19 | 9.5 | 0
|  | Ideal Trend | 48 | 43.2 | 38.4 | 33.6 | 28.8 | 24 | 19.2 | 14.4 | 9.6 | 4.8 | 0
Note on E5: Note: Effort calculated using Story Points assigned at Sprint Planning - Enter as a positive Integer
Note on S8: If something is missing at the start of Sprint Planning, place this color box in column E to indicate it was added after the start of the Sprint.
Note on S9: Format the cell of the day that a missing item was added to the Sprint with this color and add in an estimate of story points for the item.

## Sprint 2
SWE 443 - TEAM BLUE
SPRINT BURNDOWN CHART
|  |  |  | Week 1 |  |  |  |  | Week 2
| Backlog Item ID | User Stories / Bugs |  | 2017-04-19 | 2017-04-20 | 21-23 Apr | 2017-04-24 | 2017-04-25 | 2017-04-26 | 2017-04-27 | 28-30 Apr | 2017-05-01 | 2017-05-02
|  |  | Initial Estimate | Wed | Thurs | Weekend | Mon | Tues | Wed | Thurs | Weekend | Mon | Tues | Result
| 1 | Finalizing Presentation Plans (Scripts/Scenarios/Bug Fixing) | 3 | 3 | [9 empty] | Done | Legend
| 2 | Last minute adjustments to Android app for demo | 12 | 12 | [9 empty] | Done
| 3 | Continue Integrating Completed Code to Android GUI | 0.5 |  |  |  | 0.5 | [6 empty] | Done |  |  | Missing at Start
| 4 | Networking | 13 |  |  |  | 8 | 5 | [5 empty] | Done |  |  | Added to Sprint
| 5 | Password Hashing | 5 | [7 empty] | 2 | 3 |  | Done
| 6 | Scenario Writing | 0.5 |  |  | 0.5 | [7 empty] | Done
| 7 | Rewriting Tests | 6 |  |  |  |  | 0.5 | [5 empty] | Incomplete
| 8 | Enforce Strong password | 1 |  |  | 1 | [7 empty] | Done
| 9 | QR Implementation | 5.5 |  |  |  |  | 1 | 2 | 2.5 |  |  |  | Done | Hours in Sprint
| 10 | QR Research | 1 |  |  |  |  | 1 | [5 empty] | Done |  | Initial Estimate: |  | 86.5
| 11 | Enforce timeout (from idling) | [11 empty] | To Do |  | Added Hours: |  | 0
| 12 | Architecture Report | 8 |  |  |  |  | 1 | 0.25 |  | 6.75 |  |  | Done | Total Hours this Sprint: |  |  | 86.5
| 13 | Validation on Create Account (Regex) | 4 |  |  |  |  | 0.5 | 1 | 1.5 | 0.5 |  | 0.5 | Done |  |  | *not completely accurate
| 14 | Android Transaction Log | 2 | [7 empty] | 2 |  |  | Done
| 15 | Android Admin GUI | 8 | [9 empty] | 8 | Done
| 16 | General Android GUI Changes (no real estimate or task) | 7 | 4 |  |  |  | 3 | [5 empty] | Done | Progress
| 17 | Biometric Authentication | [11 empty] | To Do |  | Week 1 Progress: |  | 44.5
| 18 | Password Lockout | 2 | [9 empty] | 2 | Done |  | Week 2 Progress: |  | 36.5
| 19 | Toasts | 1 | [8 empty] | 1 |  | Done | Total Progress: |  |  | 81
| 20 | Burndown Chart Updating/Other Scrum Master Tasks | 7 | 0.5 | 0.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1.5 | 0.5 | 0.5 | Done |  |  | *not completely accurate
|  | Remaining Hours | 86.5 | 67 | 66.5 | 63.5 | 54.5 | 42 | 38.25 | 33.75 | 21 | 16.5 | 5.5
|  | Ideal Trend | 86.5 | 77.85 | 69.2 | 60.55 | 51.9 | 43.25 | 34.6 | 25.95 | 17.3 | 8.65 | 0
Note on E5: Note: Effort calculated using Story Points assigned at Sprint Planning - Enter as a positive Integer
Note on S8: If something is missing at the start of Sprint Planning, place this color box in column E to indicate it was added after the start of the Sprint.
Note on S9: Format the cell of the day that a missing item was added to the Sprint with this color and add in an estimate of story points for the item.

## Final Sprint
SWE 443 - TEAM BLUE
SPRINT BURNDOWN CHART
|  |  |  | Week 1 |  |  |  |  | Week 2
| Backlog Item ID | User Stories / Bugs |  | 2017-05-03 | 2017-05-04 | 5-7 May | 2017-05-08 | 2017-05-09 | 2017-05-10 | 2017-05-11
|  |  | Initial Estimate | Wed | Thurs | Weekend | Mon | Tues | Wed | Thurs | Result
| 1 | Transaction Fees | 8 | 2 | 5 | 1 |  |  |  |  | Done | Legend
| 2 | General Admin GUI Changes | 2.5 |  |  | 2.5 |  |  |  |  | Done
| 3 | Transaction Log | 8 | 8 | [6 empty] | Done |  |  | Missing at Start
| 4 | Set Fee - Admin | 2 |  |  | 2 |  |  |  |  | Done |  |  | Added to Sprint
| 5 | Enforce Timeout (from idling) | 1 |  | -1.5 | 2.5 |  |  |  |  | Done
| 6 | End to End Encryption | 5 |  |  |  |  | 5 |  |  | Done
| 7 | Final Presentation Scenario | 2 |  | 1.5 |  |  | 0.5 |  |  | Done
| 8 | Create Markdown READMEs where necessary | 2 |  |  |  | 0.5 |  | 1.5 |  | Done
| 9 | Final Presentation Preparation (slideshow, setup, etc) | 16 |  |  |  | 8 | 1 | 7 |  | Done | Hours in Sprint
| 10 | Transaction Log - Admin | 5 |  | 5 | [5 empty] | Done |  | Initial Estimate: |  | 77
| 11 | Dispute Transaction | [8 empty] | To Do |  | Added Hours: |  | 1.5
| 12 | Biometrics | 8 | [5 empty] | 8 |  | Done | Total Hours this Sprint: |  |  | 78.5
| 13 | Present! | 1 | [6 empty] | 1 | Done |  |  | *not completely accurate
| 14 | [9 empty] | -
| 15 | [9 empty] | -
| 16 | [9 empty] | - | Progress
| 17 | [9 empty] | - |  | Week 1 Progress: |  | 60
| 18 | GUI Changes (no set estimate) | 9 | 1 |  |  | 8 |  |  |  | Done |  | Week 2 Progress: |  | 18.5
| 19 | App Stability fixes (no set estimate) | 3 |  |  | 3 |  |  |  |  | Done | Total Progress: |  |  | 78.5
| 20 | Burndown Chart Updating/Other Scrum Master Tasks | 4.5 | 0.5 | 0.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | Done |  |  | *not completely accurate
|  | Remaining Hours | 77 | 65.5 | 55 | 42.5 | 25.5 | 18.5 | 1.5 | 0
|  | Ideal Trend | 77 | 66 | 55 | 44 | 33 | 22 | 11 | 0
Note on E5: Note: Effort calculated using Story Points assigned at Sprint Planning - Enter as a positive Integer
Note on P8: If something is missing at the start of Sprint Planning, place this color box in column E to indicate it was added after the start of the Sprint.
Note on P9: Format the cell of the day that a missing item was added to the Sprint with this color and add in an estimate of story points for the item.